## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Matthew | Josh | Michael | Colby | Total
|  | Task | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary Tasks
Iteration 1: | Architecture |  |  |  |  | 12 |  | 8 |  |  |  |  | 8
|  | Design architecture | Project Manager | Matthew, Josh | 12 |  | 8 |  | 6 | 2 |  |  | 8
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 8.5
|  | Gather | Requirements Engineer | Matthew, Josh, Michael, Colby | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Analyze | Requirements Engineer | Matthew, Josh | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Specify | Requirements Engineer | Matthew, Josh | 3 |  | 3 |  | 1.5 | 1 |  |  | 2.5
| Documentation |  |  |  |  | 16 |  | 15 |  |  |  |  | 19
|  | Project Charter | Project Manager | Matthew, Josh | 1 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Release Plan | Project Manager | Michael, Colby | 2 |  | 2 |  | 1 | 1 | 1 | 1 | 4
|  | Requirements Document | Project Manager, Requirements Engineer | Matthew, Josh | 4 |  | 3 |  | 1 | 1 | 1 | 1 | 4
|  | Project Plan | Project Manager, Developers | Michael, Colby, Matthew, Josh | 5 |  | 5 |  | 1.5 | 1 | 2 | 1.5 | 6
|  | Architecture Document | Architect | Josh, Colby | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Coding
Iteration 1: | Development |  |  |  |  | 50 |  | 50 |  |  |  |  | 36.5
|  | Determine technology needs | Developer | Matthew, Josh | 1 |  | 1 |  | 0.5 | 0.5 |  |  | 1
|  | Research and learn new language and environment (C#, .NET framework, MVC) | Developer | Josh, Michael, Colby | 15 |  | 15 |  |  | 5 | 5 | 5 | 15
|  | Write frontend code (HTML, CSS, JS) | Developer | Matthew, Josh, Michael, Colby | 8 |  | 8 |  | 2 |  | 2 | 2 | 6
|  | Create models for MVC views | Developer | Matthew, Colby | 4 |  | 4 |  | 2 |  |  | 2 | 4
|  | Implement helper classes for HTML | Developer | Colby, Michael | 2 |  | 2 |  |  |  | 1 | 1 | 2
|  | Write code to handle individual user accounts | Developer | Michael, Josh, Matthew | 7 |  | 7 |  | 2 |  | 2.5 |  | 4.5
|  | Create database from sample data | Developer | Josh, Michael | 6 |  | 6 |  |  |  | 3
|  | Write connector code to access database | Developer | Josh, Matthew | 3 |  | 3 |  | 2 |  |  | 2 | 4
|  | Unit Testing | Developer | Matthew, Colby | 4 |  | 4 | [5 empty] | 0
| Analysis |  |  |  |  | 6 |  | 6 |  |  |  |  | 8
|  | System Testing | Tester | Colby, Michael | 2 |  | 2 |  |  |  | 1 | 1 | 2
|  | Bug fix as required | Tester, Developer | Matthew, Josh, Michael, Colby | 2 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
|  | Evaluate needs for next iteration | Project Manager | Matthew, Josh | 2 |  | 2 |  | 1 | 1 | 1 | 1 | 4
Iteration 2: | Development |  |  |  |  | 12 |  | 4.5 |  |  |  |  | 13
|  | Create Database Schema | Developer | Josh, Colby | 2 |  | 1.5 |  |  | 1 |  | 0.5 | 1.5
|  | Insert Data Into Tables | Developer | Michael | 2 |  | 4 |  |  | 3 | 1 |  | 4
|  | Create Models that Match Tables | Developer | Josh | 3 |  | 0 | [5 empty] | 0
|  | Create View for Login | Developer | Matthew | 1 |  | 1 |  | 1 |  |  |  | 1
|  | Create View for Transaction History | Developer | Matthew | 3 |  | 2 |  | 2 |  |  |  | 2
|  | Create View for Adding Goal | Developer | Matthew | 1 |  | 4.5 |  | 2 |  | 2.5 |  | 4.5
| Analysis |  |  |  |  | 10 |  | 5 |  |  |  |  | 5
|  | System Testing | Tester | Colby, Michael | 4 |  | 1 |  |  |  | 0.5 | 0.5 | 1
|  | Evaluate needs for next iteration | Project Manager | Matthew, Josh, Michael, Colby | 2 |  | 2.5 |  | 1 |  | 1 | 0.5 | 2.5
|  | Bug fix as required | Tester, Developer | Matthew, Josh, Michael, Colby | 4 |  | 1.5 |  | 1 | 0.5 |  | 0 | 1.5
Iteration 3: | Development |  |  |  |  | 19 |  | 2 |  |  |  |  | 18
|  | Mesh Account will Goals | Developer | Matthew, Josh | 2 |  | 3 |  | 2 |  | 1 |  | 3
|  | Incorportate User/Goal Statistics | Developer | Michael, Colby | 3 |  | 0 |  |  | 0 |  | 0 | 0
|  | Connect Databases | Developer | Matthew, Josh | 3 |  | 2 |  | 1 |  | 1 |  | 2
|  | View Controller Tables | Developer | Matthew, Josh | 3 |  | 3 |  | 1 |  | 2 |  | 3
|  | View Statistics Tables | Developer | Michael, Colby | 6 |  | 5 |  |  | 2 |  | 3 | 5
|  | Account Manager | Developer | Matthew | 2 |  | 5 |  | 2 | 1 | 2 |  | 5
| Analysis |  |  |  |  | 9 |  | 0 |  |  |  |  | 8.5
|  | System Testing | Tester | Colby, Michael | 3 |  | 2 |  | 0 | 1 | 0 | 1 | 2
|  | Evaluate needs for next Iteration | Project Manager | Michael, Matthew, Josh, Colby | 2 |  | 4 |  | 2 | 1 | 0.5 | 0.5 | 4
|  | Bug Fix as required | Tester, Developer | Michael, Matthew, Josh, Colby | 4 |  | 2.5 |  | 1 | 0.5 | 0.5 | 0.5 | 2.5
Iteration 4: | Development |  |  |  |  | 12 |  | 0 |  |  |  |  | 0
|  | Gamification | Developer | Josh, Colby | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Layout of Chapters | Developer | Michael | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Data Layer - with entities | Developer | Matthew | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Return back to the controller | Developer | Matthew | 1 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | User Stats | Developer | Michael | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | User Documentation | Developer | Michael | 3 |  | 0 |  | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 10 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester | Colby, Michael | 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Matthew, Josh, Michael, Colby | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0
|  | Bug fix as required | Tester, Developer | Matthew, Josh, Michael, Colby | 4 |  | 0 |  | 0 | 0 | 0 | 0 | 0